## Sheet1
Task | Status | External Dependency | Notes / Comments
Necessary permissions in CIO AWS Account | Pending/In Progress | CIO IAM/Admin teams | IAM roles, cross-account access setup
Infra setup in CIO Account using TFE Workspaces | Pending/In Progress | Terraform Enterprise Team | Includes VPC, Subnets, Security Groups, etc.
Deploying EKS cluster in CIO AWS Account | Pending/In Progress | CIO Cloud/Infra team | Private EKS Cluster setup
Jenkins pipeline to build latest Keycloak images | Not Started | Jenkins Admin / DevOps Team | Dockerfile + CI pipeline setup
Jenkins pipeline to fetch latest Helm charts (Keycloak, cert-manager, ingress-nginx) | Not Started | Chart repositories | CI pipeline integration
Deploy certificate manager via Jenkins pipeline | Not Started | cert-manager maintainers | Helm chart deployment
Deploy ingress-nginx via Jenkins pipeline | Not Started | ingress-nginx repo | Helm chart deployment
Deploy Keycloak Helm chart inside test EKS cluster | Not Started | Jenkins pipelines | Deploy on newly created EKS
FNFIS service accounts configuration | Pending | FNFIS Team | Access to FNFIS APIs
HashiCorp Vault configuration | Pending | Security Team / Vault Admins | Secrets management integration
Harness setup (organization-level) | Pending/In Progress | Harness Admin | Harness project/config setup
Deploy Harness Delegate in CIO EKS cluster | Pending | Harness Team | Install Delegate in private EKS cluster
Configure/setup LDAP in new CIO AWS Account | Pending | LDAP Admins | Connectivity & integration testing
Deploy NLB & ALB Load Balancers | Not Started | Network Team | For external/internal Keycloak exposure
Configure Akamai for new Keycloak URL | Pending | Akamai Team | DNS & CDN configuration
Internal testing of Keycloak in test env | Not Started | QA/Test Team | Validate app functionality
Data migration (non-prod to CIO Account) | Not Started | Database Admins | Export/Import of Keycloak DB
Deploy to Dev & Non-Prod EKS clusters | Not Started | Jenkins pipelines | Promote to additional environments
Customer testing in non-prod environment | Pending | Customer teams | Formal UAT process
Production deployment planning | Not Started | Release Managers | Cutover checklist, timing, approvals
Production data migration | Not Started | DBA Team | Careful migration, downtime coordination
Final client testing with new URL | Pending | Client teams | Acceptance sign-off post-migration
Performance/load testing – Prior to prod cutover | To be planned | Performance/QA Team | Test Keycloak scalability and load
Compliance checks – Verify compliance requirements (e.g., audit trails, logging) | To be planned | Compliance & Security Teams | Align to regulatory standards
Stakeholder communication plan | To be planned | Project/Release Managers | Inform all stakeholders before each critical phase
Backup strategy for existing Keycloak DB | To be planned | DBA Team | Full backup before prod cutover
Disaster recovery/rollback plan | To be planned | All teams | Ensure rollback path for prod migration
DNS Cutover & Akamai switchover for prod | To be planned | DNS/Akamai Team | Actual switchover to new URL
Secrets migration (Vault or Secrets Manager) | To be planned | Security Team | Ensure secrets are ported securely
Monitoring & alerting setup for Keycloak in CIO Account | To be planned | DevOps/Monitoring team | CloudWatch, Grafana, Prometheus setup